Progress Report: January - June 2006

Northeast Consortium:  [Specifics are mentioned because, with very few exceptions, each dataset submitted for serving requires a LOT of massaging before it can go on-line.  The Data Management Office walks a fine line between encouraging the data submitter to submit their data and requiring certain data quality standards.] 

Data submitted but not servable without a lot of data processing/programming work: 

· 4” ring scallop data (Dana Morse) – Excel worksheets that are mostly blank cells.  I can serve summary data, but must rewrite spreadsheet to do it.  (Could serve “as is”.)

· Benthic correlates – fish (Michelle Dionne) – I asked for the latest version of the data and she said she’d send it.  It’s been a couple of weeks.

· Mike Pol’s gillnet length frequency data. (Could serve “as is”.)

· Trawl Taper data (Dana Morse) – Excel worksheets that are mostly blank cells.  I can serve summary data, but must rewrite spreadsheet to do it. (Could serve “as is”.)


Created Inventory of Northeast Consortium projects to serve as the master data entry point.  This was where most of the effort of 2006 went and is going.   “If you don’t know where to start, start with the Inventory.”  This inventory of data complements the NEC project database.  Every project has an entry regardless of status of data submission and each project in turn is linked to a category in the data system.  There are 140 projects in the Inventory.  (Project database has 191.  We’re pursuing the discrepancy.)  The place holding effort for those projects with no submitted data is ongoing and should be completed soon.  Metadata records for each project have been created and are linked to each data object.  
(Items in red are pre-January)


Partnership for Pelagic Ecosystem Monitoring in the Gulf of Maine (PULSE):

· CTD:  added 2005 data.
· Chlorophyll:  Added 2005 data.

· Zooplankton:  Waiting to make 2005 data public.

· Worked with Rebecca Jones, UNH.


Benthic Habitat Correlates:
· Finally finished this dataset for invertebrates only and served.
· Worked with Michelle Dionne, Wells National Estuarine Research Reserve and Chris Manning, Northeast Consortium, UNH.


eMOLT: 

· Upgraded links.  Work in progress to serve data directly.

· Attempting to serve drifter data.

· Worked with Jim Manning, NMFS, Woods Hole.


Habitat/Ecology:

· Added new data object:  Lobster Tagging, Tracking and Recapture Data (5 data objects including temperature study)

· New data object.  Pilot Gillnet survey of the Cashes Ledge Closed Area.

· New data set (two data objects): Environmental Contaminants (metals) and Environmental Contaminants (PCBs and Pesticides) on Stellwagon Bank

· Worked with Diane Cowan, the Lobster Conservancy; Kevin Kelly, Maine DMR; Emily Monosson, Mt. Holyoke College; Rachel Gallant, Northeast Consortium, UNH.


Gear Technology:

· New data object.  Bycatch reduction in the NE Shrimp fishery.

· New data object.  Comparison of Beam and otter trawls in NE Shrimp fishery

· New data object.  Feasibility study for knotless codends.  Includes separate object for movies of gear in use.
· New data set.  Testing of Low-Profile, Low Cod-bycatch gillnets.  Includes catch comparisons, configuration detail summary, and temperature data from loggers attached to nets.  Three data objects.

· Worked with Bill Lee, Captain, F/V Ocean Reporter, Rockport, ME; Kelo Pinkham, F/V Jeanne C.; Mike Pol, Massachusetts Div. Marine Fisheries; Alan Michael, ADM Associates.


Fish Biology:

· New data object.  Trophic Ecology of Atlantic Cod – 4 years of data (2001-2004)

· Worked with Frank Almeida, NMFS/NFSC; Chris Manning, UNH.


Other:  Worked to seamlessly integrate with NEC when they changed their website.  
Effort is ongoing to improve user interface to NEC data.  Work is ongoing to clean up the 
on-line data and make the fieldnames consistent. 
